08/08/2006 IPG Meeting Minutes

Attendees:

Carla Beaudet, John Ford, Frank Ghigo, Randy McCullough, Chuck Niday, David Woody, Paulette Woody

- Richard has been calling RFI group/ EPO group /Business Office meetings to enhance coordination between groups. Please attend if invited, IPG needs to be adequately represented.

Emphasis made on attendance to the meeting if requested.

- Zone 1 progress

  - GBT Actuator Controller Covers

    - Dave Woody/Nathan Sharp have begun installation. This is a long-term “fill-in” project, due to GBT access required.

- Three covers completed to date.

- Delay due to alignment issues on the racks, a retro-fit is progress.

- Covers being installed when available and with GBT access.

- Expected completion date of summer 2007.

- Discussion: Shielding of actuator controls with and without proper hardware.

  - 3.6m Dish Mount and Az/El controller

    - Shop plans to start work on motor covers this week.

- Last fabrication step prior to testing and installation.

  - GBT RFI Monitoring Station

    - Still to be done:

      - Continued troubleshooting of Az/El calibration issue

      - Pressurize damper bearing

- Not completed or tested.

      - Complete system check-out

- Corrosion has been found.

- Possible design issue.

- ACTION ITEM: C. Beaudet with J. Ford and R. McCullough offering assistance. Positioning.

  - “Show Me” project (digital camera detection) complete; results support Zone 1 policy.

- Tests completed and report posted on web site.

- Test confirmed policy.

- Discussion: Concerning electronic devices currently being sold at the Science Center.

- Zone 2

  - Indoor signage for visitor center and busses temporarily removed; in meeting w/ Richard and EPO, EPO wanted time to integrate “new” policy RE digital cameras into their own tourist literature, which currently reads “cameras permitted”.

  - Signs will be installed prior to next year’s tourist season.

  - EPO also wants a RFI bunker or reflector w/ R. C. Byrd sign moved to good photo location. Please, somebody volunteer to work on this.

- Project “Duck Blind”. Possible EPO funding with the RFI Group to design and build.

- Discussion: Concerning shielding and construction.

- Zones 3, and 4:

  - In consultation with Rick Fisher, Richard has decided to delay approaching the public with a brochure or anything else before contact with elected state officials. We would like financial support for acting on the RA Zoning Act as pertains to the public (Funds to assist private citizens in the immediate vicinity.) This “freeze” directive to our group pertains only to the public and not to Zone 3/4 issues w/corporate entities.

- RFI Group to not approach public directly until upper Management has proceeded with their policy plan.

- Urge upper Management to proceed without delay.

- Discussion: Funding not just for promotional materials, but also if available for other electronic device replacement and the burial of power lines in vicinity of Observatory.

- Discussion: Resources available to be in the interest of GB issues.

  - Frontier Communications Letter

    - Have made contact with Greg Sayer, Frontier Lawyer. Says Frontier is willing to work with us to come up with a solution that will work; needs coverage maps for 2.4 GHz.

- Wireless modems are the property of Frontier.

- Review of current letter puts responsibility on customer, not Frontier.

- ACTION ITEM: W. Sizemore. Coverage map completion.

- Frontier is considering recalling modems and providing a replacement model.

- Discussion: Blue tooth devices as a wireless modem alternative.

- Zone 5:

  - TAP Issues

  - Obstacle size discrepancies.

  - Propagation Model Campaign Progress

- Moving forward.

- Grad student has visited GB and provided ideas for the path studies. The details of which were outlined in a RFI Group meeting with student.

- Funding provided by Navy.

- Discussion within group concerning elevation verification, GPS comparisons.

- Trimble to be onsite on 09 AUG for a demonstration.

  - Discussion: Concerning Dr. Brown and the Navy involvement.

  - Other issues?

  - Receiving good cooperation with Federal entities.

- Other Issues

  - Pendleton Co. Wind Turbines

    - Neither NRQZ nor RA Zoning Act applies

    - No way to evaluate w/o emissions test results

- Senator Byrd had sent letter to GB business office.

    - Discussion: On the intent of this inquiry.

  - Anything Else?

- Interference on 1965 MHz

Next meeting scheduled for September 12, 2006.

12 SEPT 06 meeting cancelled. Rescheduled for 14 SEPT 06.